## All Checks
Item	Stage	Tags	Result	Commit	Notes
Double Check Decoupling Capacitor placement	PCB Layout			7501b38e1c74a69f89ae33cc145d99332150d204
JTAG/SWD Pads + Interface PCB	PCB Layout		First Pass Done
Perform FEM to check: / + Noise induced on ADC lines / + Return paths	PCB Layout	FEM
Return Current Analysis	PCB Layout
Pass DRC	PCB Layout
Find out good attach/release mechanism for Thermo Couples	PCB Layout
Check Oscillator Design Guide for PCB	PCB Layout
Layout guidelines for 60V Parts	PCB Layout
VBAT Decoupling Cap close-ish?	PCB Layout
Do Oscillator Design	PCB Layout		First Pass Done	4f5d612732d318e6d1cdf057fe1d47e9154a4850	Parasitics still have to be calculated/measured
Compare with Phil’s Lab PCB	PCB Layout
Oscillator: Calculate Parastics	PCB Layout	Oscillator
Check Impedance of USB Differential Pair (50 Ohm Single Ended)	PCB Layout	USB
Figure out Power Delivery	PCB Layout		First Pass Done	467e2ad2b15cc481dac560d4886342b068afb24b
Design Rule: Equal Spacing between Traces	PCB Layout
Design Rule: Partition PCB into distinct regions (Power,Analog, Digital, Connectors)	PCB Layout
Design Rule: Place Test Points	PCB Layout
Design Rule: Symmetrical Design	PCB Layout
Design Rule: Not Sharp Edges/Corners on Edge Cuts	PCB Layout
Design Rule: Polarity Indicators for Diodes + Pin 1 Silkscreen	PCB Layout
Confirm Voltage Dividers of Thermo Couples	Pre First Boot
Confirm Voltage Output of Voltage Regulator	Pre First Boot
Confirm Voltage range of VBUS	Pre First Boot
UART over USB	Pre Order
Ensure Clearance of Components	Pre Order
Calculate Resonator Capacitances	Schematic		First Pass Done	4f5d612732d318e6d1cdf057fe1d47e9154a4850	See Spreadsheet Oscillator_Selection.ods
JTAG/Serial Wire Debug Pinout	Schematic		First Pass Done	7501b38e1c74a69f89ae33cc145d99332150d204	https://developer.arm.com/documentation/101636/0100/Debug-and-Trace/JTAG-SWD-Interface
Confirm Voltage Range of ThermoCouples	Schematic
Confirm Pinout with STM CubeIDE	Schematic
Calculate Voltage Regulator Capacitor for EN Drain Time	Schematic
SD Card storage device	Schematic
Pass ERC	Schematic
Should VBAT be connected?	Schematic		First Pass Done	f9281afe62da5ec8378b19c2370bab044c28db71	it is recommended to connect this pin to V DD with a 100 nF / external ceramic decoupling capacitor. (an4488 page 9)
Does USB ID Have to be connected for Child only mode	Schematic
Consider using a Toggle for the NRST pin → Reduce BOM Parts	Schematic		First Pass Done	eb2a949a54a4c0c3f6096d2d67ab4c95599eb6d5
Temperature Reference Thermistor	Schematic
Correct Voltage Divider for Thermo Couples	Schematic
Oscillator: Needs HSE Oscillator	Schematic	Oscillator	First Pass Done	4f5d612732d318e6d1cdf057fe1d47e9154a4850	USB OTG FS requires a HSE (stm32f401rb.pdf page 30)
Get PCB + Trace Parasitics	Schematic	Oscillator
Check Footprint Pin Assignments and Dimensions	Schematic