## All Checks
Item	Stage	Result	Commit	Notes
Double Check Decoupling Capacitor placement	PCB Layout		7501b38e1c74a69f89ae33cc145d99332150d204
JTAG/SWD Pads + Interface PCB	PCB Layout	First Pass Done
Perform FEM to check: / + Noise induced on ADC lines / + Return paths	PCB Layout
Return Current Analysis	PCB Layout
Pass DRC	PCB Layout
Find out good attach/release mechanism for Thermo Couples	PCB Layout
Check Oscillator Design Guide for PCB	PCB Layout
Improve Layout	PCB Layout
Layout guidelines for 60V Parts	PCB Layout
VBAT Decoupling Cap close-ish?	PCB Layout
Do Oscillator Design	PCB Layout	First Pass Done	4f5d612732d318e6d1cdf057fe1d47e9154a4850	Parasitics still have to be calculated/measured
Compare with Phil’s Lab PCB	PCB Layout
Oscillator: Calculate Parastics	PCB Layout
Confirm Voltage Dividers of Thermo Couples	Pre First Boot
Confirm Voltage Output of Voltage Regulator	Pre First Boot
Confirm Voltage range of VBUS	Pre First Boot
UART over USB	Pre Order
Ensure Clearance of Components	Pre Order
Calculate Resonator Capacitances	Schematic	First Pass Done	4f5d612732d318e6d1cdf057fe1d47e9154a4850	See Spreadsheet Oscillator_Selection.ods
JTAG/Serial Wire Debug Pinout	Schematic	First Pass Done	7501b38e1c74a69f89ae33cc145d99332150d204	https://developer.arm.com/documentation/101636/0100/Debug-and-Trace/JTAG-SWD-Interface
Confirm Voltage Range of ThermoCouples	Schematic
Confirm Pinout with STM CubeIDE	Schematic
Calculate Voltage Regulator Capacitor for EN Drain Time	Schematic
SD Card storage device	Schematic
Pass ERC	Schematic
Should VBAT be connected?	Schematic	First Pass Done	f9281afe62da5ec8378b19c2370bab044c28db71	it is recommended to connect this pin to V DD with a 100 nF / external ceramic decoupling capacitor. (an4488 page 9)
Does USB ID Have to be connected for Child only mode	Schematic
Consider using a Toggle for the NRST pin → Reduce BOM Parts	Schematic
Temperature Reference Thermistor	Schematic
Correct Voltage Divider for Thermo Couples	Schematic
Oscillator: Needs HSE Oscillator	Schematic	First Pass Done	4f5d612732d318e6d1cdf057fe1d47e9154a4850	USB OTG FS requires a HSE (stm32f401rb.pdf page 30)
Get PCB + Trace Parasitics	Schematic
Check VSSA/VSS Gap with regards to Return Currents and EMF	PCB Layout
Figure out Power Delivery	PCB Layout